## Task Schedule
Deadline | Who | Task | Status
PROJECT PROPOSAL DRAFT
2021-09-07 | Brenna | PM: Turn in meeting minutes. | Completed
2021-09-07 | Brenna | PM: Tell project team how to find meeting minutes (and future minutes.) | Completed
2021-09-07 | Brenna | PM: Create a meeting for Wednesday at 5:30pm and include an agenda. | Completed
2021-09-07 | Brenna | PM: Create a rough draft of the task schedule. | Completed
2021-09-07 | Brenna | PM: Draft a straw document using the above notes. | Completed
2021-09-11 | Michelle | Submit Cover Page DRAFT by 5PM | Completed
2021-09-11 | Liesl | Submit Executive Summary DRAFT by 5PM | Completed
2021-09-11 | Brenna | Submit Current Situation DRAFT by 5PM | Completed
2021-09-11 | Michelle | Submit Specific Objectives DRAFT by 5PM | Completed
2021-09-11 | Samuel | Submit Deliverables Overview DRAFT by 5PM | Completed
2021-09-11 | Everyone | Submit Personnel Qualifications DRAFT by 5PM | Completed
2021-09-11 | Liesl | Submit Conclusion DRAFT by 5PM | Completed
2021-09-12 | Everyone | Review and comment on draft submissions by 5 PM | Completed
2021-09-13 | Everyone | Meet to review individual submissions and assemble final draft | Completed
2021-09-14 | Everyone | Turn in final draft in CANVAS by 11:30AM and email everyone with a screenshot to show it was done | Completed
PROJECT PROPOSAL REVISION
2021-09-22 | Liesl | Aggregate all feedback from Peer Reviews onto Proposal document for editing | Completed
2021-09-23 | Brenna | Edit proposal document | Completed
2021-09-29 | Everyone | Discuss Brenna's edits to Proposal | Completed
2021-10-05 | Brenna | Turn in Proposal Revision with memo to Dr. Hodges | Completed
2021-11-21 | Everyone | Third Round Proposal Revision | Completed
PROJECT PLAN
2021-09-17 | Brenna | Create Project Plan and tag Group for review | Completed
2021-09-24 | Brenna | Turn in Project Plan to Dr. Hodges | Completed
2021-10-05 | Brenna | Turn in revised Project Plan with memo to Dr. Hodges | Completed
DATA GATHERING PHASE
2021-09-23 | Liesl/Samuel | Deliver draft of "Quality Assurance metric or questions" for Website QA for Group review | Completed
2021-09-23 | Michelle/Samuel | Deliver draft of Survey Questions for Group review | Completed
2021-09-29 | Everyone | Meet to review Survey Questions and Website QA Metric/Questions, Project Proposal Revision | Completed
2021-09-29 | Everyone | Gather volunteers for surveys and Website QA | Completed
2021-09-29 | Michelle/Samuel | Start Survey and send to student volunteers | Completed
2021-09-30 | Liesl/Samuel | Conduct Website QA with student volunteers | Completed
2021-10-08 | Liesl/Samuel/Michelle | Stop Surveys and Website QA | Completed
2021-10-08 | Everyone | Meet to examine All Data Gathered | Completed
GROUP PRESENTATION PHASE
2021-10-08 | Everyone | Meet to discuss what should go into the Presentation | Completed
2021-10-08 | Brenna | Update Project Plan and Meeting Minutes | Completed
2021-10-08 | Liesl/Michelle | Assemble and design the Presentation | Completed
2021-10-10 | Liesl/Michelle | Draft of Presentation Due | Completed
2021-10-10 | Everyone | Meet to Review and Work on Group Presentation | Completed
2021-10-14 | Everyone | Slide designs due | Completed
2021-10-15 | Everyone | Meet to talk about presentation segments | Completed
2021-10-15 | Brenna | Assemble Final Presentation Video | Completed
2021-10-19 | Everyone | Group Presentation for Practice | Completed
2021-10-20 | Everyone | Meet to rework Presentation? | Completed
2021-10-21 | Brenna | Add 2 other Website Analyses to Presentation | Completed
| Everyone | Re-Record Presentations | Completed